## README
Last Update | 2019-10-14
Author | Brandon Abutin, Itzel Gonzalez, Jiunn Siow, Bryan Delgado, Parth Mangrola
Email | babut001@ucr.edu
Description | CryptoCurrency Web Application
Summary / Requirements | This spreadsheet serves two purposes: (1) for your team to track progress during your sprints, and (2) as a record of what user stories were implemented, in which tasks, and by whom. For (1), if you prefer to use an alternate tool to track progress as you go (e.g., Trello), that is fine. However, for (2), it is critical that you keep the "Product Backlog" and "Archives" up to date, at least at the end of each sprint. Also, note that if the number of estimated points for a story ends up being very inaccurate (i.e., if the user story took much more or much less effort than expected), please update the story points estimate and give a comment explaining the adjustment.
Sprint 1 | Notes | Story Points
Product Backlog | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means to be "Done"

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
1. Landing Page(Itzel,Bryan,Parth)
1a. Register User Account(Bryan)
1b. Backend logic for registering user account (Brandon)
1c. Pop up, section to login(Itzel)
2. Password Update(Parth,Brandon,Bryan)
2a. Pop up, section to update password (Parth,Bryan)
2b. Backend Logic for Updating Password (Brandon,Bryan)
3. View List of Cryptocurrencies(Parth&Jiunn)
3a. Back End for List of Cryptocurrency(Jiunn,Parth)
3b.Front end for list of cryptocurrencies(Jiunn,Parth)
3c. Sort the List through a button(Highest and lowest price)(Jiunn)
4. Check the price of Cryptos(Jiunn)
4a. User is able to select/view specific crypto to view info (Jiunn)
4b. Back End display info on seperate page(Jiunn)
5. Get news about cryptocurrencies(Brandon)
5a. Back End- API call to get news(Brandon)
5b. Front End- create new routing page for individual cryptocurrency(Brandon)
6. Conversion Calculator (Itzel,Parth)
6a. Front end make slot for user to enter amount of coins or USD(Itzel,Parth)
6b. Back End logic to make conversion (Itzel,Parth)
6c. Front End Display Output (Itzel,Parth)
7. Choose favorite currencies to follow(Itzel and Bryan)
7a. Front End: Make "favorite" button next to each cryptocurrency (Jiunn)
7b. Backend: Add favorite to user account(Bryan)
7c. Display favorites in navbar drop down page(Bryan)
7d.Alerts for cryptocurrencies
8. Personal information page for each currency (Parth)
8a. Front end to display coin description and links (Parth)
8b. Back end API gets info (Parth)
9. Search Bar (Brandon)
9a. Look up different currencies and be sent to their respective page (Brandon)

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
1 | Register User Account | As an unregistered User, I want to register for an account so that I can login/logout and get personalized updates on my favorite cryptocurrencies. | 3 | 1 | Split between front-end & back-end
2 | Password Update | As a registered user, I want to edit my password so that I can update it based on my needs. | 2 | 2 | Split between front-end & back-end
3 | View list of cryptocurrencies | As a user, I want to be able to view a list of all of the current top available cryptocurrencies. | 2 | 3 | Split between front-end & back-end
4 | Check the price of cryptocurrencies | As a user, I want to be able to view the price of a specific cryptocurrency via a graph and view changes in the price of the cryptocurrency. | 2 | 4 | Done using React
5 | Gets news about chosen cryptocurrencies | As a user, I want to see any news about a certain cryptocurrency. | 2 | 5
6 | Conversion Calculator | As a user, I want to be able to convert a certain amount of cryptocurrency to USD | 3 | 6
7 | Choose favorite currencies to follow | As a registered user, I want to be able to choose what cryptocurrencies I can follow. I want to quickly see how my favorite currencies are doing and what the current price is. | 2 | 8
8 | Personal information page for each currency | As a user, I want to be able to read information about each cryptocurrency. I want to read about the purpose of the coin and the team behind it. | 3 | 9
9 | Currency Search Bar | As a user, I want to be able to type in a coin name and search for it and be returned to that coin’s page. | 3 | 10
| Total |  | 25

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 |  | 1. Landing Page (Itzel,Bryan,Parth)
1 |  | 1a. Register User Account (Bryan)
1 |  | 1b. Backend logic for registering user account (Brandon)
1 |  | 1c. Pop up, section to login (Itzel)
1 |  | 2. Password Update (Parth,Brandon,Bryan)
1 |  | 2a. Pop up, section to update password (Parth,Bryan)
1 |  | 2b. Backend Logic for Updating Password (Brandon,Bryan)
1 |  | 3. View List of Cryptocurrencies (Bryan&Parth&Jiunn)
1 |  | 3a. Back End for List of Cryptocurrency(Jiunn,Bryan,Parth)
1 |  | 3b.Front end for list of cryptocurrencies(Jiunn,Bryan,Parth)
1 |  | 3c. Sort the List through a button(Highest and lowest price)(Jiunn)
2 |  | 4. Check the price of Cryptos(Jiunn)
2 |  | 4a. User is able to select/view specific crypto to view info (Jiunn)
2 |  | 4b. Back End display info on seperate page(Jiunn)
2 |  | 5. Get news about chosen cryptocurrencies(Brandon)
2 |  | 5a. Back End - API call to get news(Brandon)
2 |  | 5b. Front End - create new routing page for individual cryptocurrency(Brandon)
2 |  | 6. Conversion Calculator (Itzel,Parth)
2 |  | 6a. Front end make slot for user to enter amount (Itzel,Parth)
2 |  | 6b. Back End logic to make conversion (Itzel,Parth)
2 |  | 6c. Front End Display Output
3 |  | 7. Choose favorite currencies to follow
3 |  | 7a. Front End: Make "favorite" button next to each cryptocurrency ()
3 |  | 7b. Add favorite to user account (backend)
3 |  | 7c. Display favorites in navbar drop down page.
3 |  | 8. Personal information page for each currency (Parth)
3 |  | 8a. Front end to display coin description and links
3 |  | 8b. Back end API gets info
3 |  | 9. Search Bar(Brandon)
3 |  | 9a. Look up different currencies and be sent to their respective page
3 |  | 9b. Have option to "favorite" returned search values

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 25 |  |  | 25 | 25
1 | 25 | 0 | 0 | 25 | 18
2 | 25 | 14 | 14 | 11 | 11
3 | 25 | 25 | 25 | 0 | 0